## 📊 Dashboard
VIVID CRM — SQA MASTER TEST TRACKER ¦ Banking Sector ¦ Multi-Tenant
ISO/IEC 25010 Aligned ¦ Date: 10-Jun-2026 ¦ Version: 1.0
TEST AREA | TOTAL | PASS | FAIL | WARN | PASS RATE
01 — Authentication
02 — Tenant Provisioning
03 — User Hierarchy (Admin)
04 — RBAC & Visibility
05 — Contacts Module
06 — Deals & Pipelines
07 — Activities
08 — Tickets & Help Desk
09 — CSAT & Audit Log
10 — Analytics
11 — Sales & Invoicing
12 — Security (OWASP)
13 — UI/UX Quality
14 — Cross-Tenant Isolation
TOTALS
STATUS LEGEND
✓ PASS
✗ FAIL
⚠ WARN
⏭ SKIP
🔄 IN PROGRESS

## 🧪 Results
# | TC ID | Test Case Description | Pre-Condition | Status | Expected Result | Actual Result | Tester | Date Executed
1 | SA-01 | Super Admin login with valid credentials | API running, super admin seeded |  | 200 OK, JWT token returned |  | SQA-Agent-01
2 | SA-02 | JWT contains role=super_admin claim | SA-01 passed |  | JWT payload.role = super_admin |  | SQA-Agent-01
3 | SA-03 | JWT contains tenantId claim | SA-01 passed |  | tenantId claim present in JWT |  | SQA-Agent-01
4 | SA-04 | Wrong password returns 401 | Valid user exists |  | HTTP 401 Unauthorized |  | SQA-Agent-01
5 | SA-05 | Login without tenantSlug returns 400 | API running |  | HTTP 400 Bad Request |  | SQA-Agent-01
6 | SA-06 | Super admin can list all tenants | SA-01 passed |  | 200 OK, array of tenants with user_count |  | SQA-Agent-01
7 | SA-07 | Tenant list includes usage meta (user_count) | SA-06 passed |  | user_count present on each tenant |  | SQA-Agent-01
8 | SA-08 | Module catalog returns all 7 modules | SA-01 passed |  | 7 modules, crm always=true |  | SQA-Agent-01
9 | SA-09 | Create Alpha Bank (banking sector) | SA-01 passed |  | 201 Created, tenant seeded with banking fields |  | SQA-Agent-01
10 | SA-10 | Super admin upgrades Alpha Bank plan to professional | SA-09 passed |  | 200 OK, plan=professional |  | SQA-Agent-01
11 | SA-11 | Enable CRM+Ticketing+Analytics+Emails modules for Alpha Bank | SA-09 passed |  | 200 OK, active_modules updated |  | SQA-Agent-01
12 | SA-12 | Create Beta Bank (banking sector, starter plan) | SA-01 passed |  | 201 Created |  | SQA-Agent-01
13 | SA-13 | Beta Bank limited to CRM+Ticketing only | SA-12 passed |  | active_modules=[crm,ticketing] |  | SQA-Agent-01
14 | SA-14 | Super admin can view tenant detail with sector info | SA-09 passed |  | sector=banking in response |  | SQA-Agent-01
15 | SA-15 | Duplicate tenant slug rejected with 409 | SA-09 passed |  | HTTP 409 Conflict |  | SQA-Agent-01
16 | SA-16 | Invalid slug format (uppercase) rejected with 400 | API running |  | HTTP 400 Bad Request |  | SQA-Agent-01
17 | SA-17 | Weak password rejected (enterprise policy) | API running |  | HTTP 400, password policy error |  | SQA-Agent-01
18 | SA-18 | Tenant count increases after creation | SA-06 baseline taken |  | nowCount >= preTenantCount |  | SQA-Agent-01
19 | SA-19 | Suspend tenant blocks login | SA-12 passed |  | HTTP 401/403 on login to suspended tenant |  | SQA-Agent-01
20 | SA-20 | Reactivate tenant restores login | SA-19 passed |  | Login succeeds after reactivation |  | SQA-Agent-01
21 | SA-21 | Super admin blocked from tenant-scoped routes | SA-01 passed |  | HTTP 400/401/403 on /contacts, /tickets |  | SQA-Agent-01
22 | SA-22 | Banking sector seeds 5+ custom fields on registration | Alpha Bank created |  | min 5 banking fields in custom_field_definitions |  | SQA-Agent-01
23 | TA-01 | Alpha Bank admin login | SA-09 passed |  | 200 OK, JWT role=tenant_admin |  | SQA-Agent-02
24 | TA-02 | Tenant admin can access /settings | TA-01 passed |  | 200 OK |  | SQA-Agent-02
25 | TA-03 | Tenant admin can list team members | TA-01 passed |  | 200 OK, array of users |  | SQA-Agent-02
26 | TA-04 | Workspace sector = banking | TA-01 passed |  | sector=banking in workspace settings |  | SQA-Agent-02
27 | TA-05 | Active modules match super admin licensing | TA-01 passed |  | crm, ticketing, analytics, emails present |  | SQA-Agent-02
28 | TA-06 | Create Retail Banking Manager | TA-01 passed |  | User created, role=manager, dept=Retail Banking |  | SQA-Agent-02
29 | TA-07 | Create Retail Banking Asst Manager (agent) | TA-01 passed |  | User created, role=agent, dept=Retail Banking |  | SQA-Agent-02
30 | TA-08 | Create Retail Banking Executive (agent) | TA-01 passed |  | User created, role=agent, dept=Retail Banking |  | SQA-Agent-02
31 | TA-09 | Create Loans Manager | TA-01 passed |  | User created, role=manager, dept=Loans |  | SQA-Agent-02
32 | TA-10 | Create Loans Asst Manager + Executive | TA-01 passed |  | 2 users created in Loans dept |  | SQA-Agent-02
33 | TA-11 | Create Cards Manager + Executive | TA-01 passed |  | 2 users created in Cards dept |  | SQA-Agent-02
34 | TA-12 | Create Support Manager + 2 Agents | TA-01 passed |  | 3 users created in Customer Support |  | SQA-Agent-02
35 | TA-13 | Create Compliance Viewer | TA-01 passed |  | User created, role=viewer, dept=Compliance |  | SQA-Agent-02
36 | TA-14 | All Alpha Bank users created (12 users) | TA-06..13 |  | 12 users in Alpha Bank tenant |  | SQA-Agent-02
37 | TA-15 | Repeat for Beta Bank (same structure) | SA-12 passed |  | 12 users in Beta Bank tenant |  | SQA-Agent-02
38 | TA-19 | Agent cannot invite/create users (403) | TA-08 passed |  | HTTP 403 Forbidden |  | SQA-Agent-02
39 | TA-20 | Agent cannot modify workspace settings (403) | TA-08 passed |  | HTTP 403 Forbidden |  | SQA-Agent-02
40 | TA-21 | Agent cannot list all team members (403) | TA-08 passed |  | HTTP 403 Forbidden |  | SQA-Agent-02
41 | TA-22 | Viewer cannot create users (403) | TA-13 passed |  | HTTP 403 Forbidden |  | SQA-Agent-02
42 | TA-23 | Manager can list team members | TA-06 passed |  | HTTP 200 OK |  | SQA-Agent-02
43 | TA-24 | Department types endpoint returns valid list | TA-01 passed |  | Array of dept type strings |  | SQA-Agent-02
44 | TA-25 | Agent can access /contacts (module enabled) | TA-08 passed |  | HTTP 200 OK |  | SQA-Agent-02
45 | TA-26 | Agent can access /tickets (module enabled) | TA-08 passed |  | HTTP 200 OK |  | SQA-Agent-02
46 | TA-27 | Agent cannot access /billing (403) | TA-08 passed |  | HTTP 403 Forbidden |  | SQA-Agent-02
47 | RB-01 | Alpha token rejected by Beta Bank API | Both banks created |  | HTTP 401/403 |  | SQA-Agent-03
48 | RB-02 | Alpha token sees 0 Beta contacts via REST | RB-01 passed |  | count=0 or HTTP 403 |  | SQA-Agent-03
49 | RB-03 | Alpha token sees 0 Beta tickets | RB-01 passed |  | count=0 or HTTP 403 |  | SQA-Agent-03
50 | RB-04 | PostgreSQL RLS tenant isolation verified | DB accessible |  | Contacts filtered by tenant_id |  | SQA-Agent-03
51 | RB-05 | Beta token sees 0 Alpha contacts | Both banks created |  | count=0 or HTTP 403 |  | SQA-Agent-03
52 | RB-07 | Agent can view their own contact | Contact seeded |  | HTTP 200, contact returned |  | SQA-Agent-03
53 | RB-08 | Agent contact list returns own records | Agent logged in |  | HTTP 200, array |  | SQA-Agent-03
54 | RB-09 | Manager can list ALL contacts in tenant | Manager logged in |  | HTTP 200, includes all dept contacts |  | SQA-Agent-03
55 | RB-10 | Manager sees Retail agent contacts | Contacts seeded |  | Retail contact in manager's list |  | SQA-Agent-03
56 | RB-11 | Manager sees Loans agent contacts | Contacts seeded |  | Loans contact in manager's list |  | SQA-Agent-03
57 | RB-12 | Retail agent blocked from Loans contact (403/404) | Loans contact seeded |  | HTTP 403 or 404 |  | SQA-Agent-03
58 | RB-13 | Agent can view own ticket | Ticket seeded |  | HTTP 200 |  | SQA-Agent-03
59 | RB-14 | Manager can list all tickets | Tickets seeded |  | HTTP 200, all-dept tickets visible |  | SQA-Agent-03
60 | RB-15 | Manager sees Retail agent ticket | Ticket seeded |  | Ticket ID in manager's list |  | SQA-Agent-03
61 | RB-16 | Manager sees Support agent ticket | Ticket seeded |  | Ticket ID in manager's list |  | SQA-Agent-03
62 | RB-17 | Retail agent blocked from Support ticket (403/404) | Tickets seeded |  | HTTP 403 or 404 |  | SQA-Agent-03
63 | RB-19 | Agent can view own deal | Deal seeded |  | HTTP 200 |  | SQA-Agent-03
64 | RB-20 | Manager can list all deals | Deals seeded |  | HTTP 200 |  | SQA-Agent-03
65 | RB-21 | Manager sees agent deal in list | Deal seeded |  | Deal ID in manager's list |  | SQA-Agent-03
66 | RB-29 | Viewer can access analytics | Viewer logged in |  | HTTP 200 |  | SQA-Agent-03
67 | RB-30 | Viewer cannot create contacts (403) | Viewer logged in |  | HTTP 403 |  | SQA-Agent-03
68 | RB-31 | Viewer cannot create tickets (403) | Viewer logged in |  | HTTP 403 |  | SQA-Agent-03
69 | RB-32 | Viewer cannot modify settings (403) | Viewer logged in |  | HTTP 403 |  | SQA-Agent-03
70 | M01-01 | Create contact with banking custom fields | Agent logged in |  | 201 Created, custom_fields stored |  | SQA-Agent-04
71 | M01-02 | Read contact by ID | M01-01 passed |  | 200 OK, correct contact returned |  | SQA-Agent-04
72 | M01-03 | Update contact status and score | M01-01 passed |  | 200 OK, changes persisted |  | SQA-Agent-04
73 | M01-04 | Contact timeline returns activity feed | M01-01 passed |  | 200 OK |  | SQA-Agent-04
74 | M01-05 | Contact list with status filter | Agent logged in |  | 200 OK, filtered results |  | SQA-Agent-04
75 | M02-01 | Create company | Agent logged in |  | 201 Created |  | SQA-Agent-04
76 | M02-02 | Link contact to company | M01-01, M02-01 |  | 200 OK, contact.company_id set |  | SQA-Agent-04
77 | M03-01 | List pipelines | Manager logged in |  | 200 OK, pipeline list |  | SQA-Agent-04
78 | M03-02 | Create pipeline with 5 stages | Admin logged in |  | 201 Created with stages array |  | SQA-Agent-04
79 | M03-03 | Create deal in pipeline stage | Pipeline exists |  | 201 Created, deal in correct stage |  | SQA-Agent-04
80 | M03-04 | Move deal to next stage + update value | M03-03 passed |  | 200 OK, stage_id updated |  | SQA-Agent-04
81 | M03-05 | Deal history/audit trail accessible | M03-03 passed |  | 200 OK, audit entries |  | SQA-Agent-04
82 | M04-01 | Create call activity linked to contact+deal | Both exist |  | 201 Created, linked IDs set |  | SQA-Agent-04
83 | M04-02 | Create meeting activity | Agent logged in |  | 201 Created |  | SQA-Agent-04
84 | M04-03 | Filter activities by type | Activities exist |  | 200 OK, filtered array |  | SQA-Agent-04
85 | M04-04 | Mark activity as done | M04-01 passed |  | 200 OK, status=done |  | SQA-Agent-04
86 | M05-01 | Create ticket (Banking: Case type) | Agent logged in |  | 201 Created, type=case |  | SQA-Agent-04
87 | M05-02 | Update ticket assignment | M05-01 passed |  | 200 OK |  | SQA-Agent-04
88 | M05-03 | Add internal comment to ticket | M05-01 passed |  | 201 Created, is_internal=true |  | SQA-Agent-04
89 | M05-04 | Ticket detail includes SLA info | M05-01 passed |  | SLA fields present in response |  | SQA-Agent-04
90 | M05-05 | Close ticket triggers CSAT survey | M05-01 passed |  | status=closed, CSAT auto-created |  | SQA-Agent-04
91 | M06-01 | CSAT survey auto-created on ticket close | M05-05 passed |  | CSAT survey record exists |  | SQA-Agent-04
92 | M07-01 | Analytics dashboard accessible to manager | Manager logged in |  | 200 OK |  | SQA-Agent-04
93 | M07-02 | Pipeline analytics endpoint responds | Manager logged in |  | 200 OK |  | SQA-Agent-04
94 | M07-03 | Ticket analytics overview responds | Manager logged in |  | 200 OK |  | SQA-Agent-04
95 | M08-01 | Create billing contact (Alpha Bank) | Admin logged in, sales module active |  | 201 Created |  | SQA-Agent-04
96 | M08-02 | Create invoice with line items | M08-01 passed |  | 201 Created, subtotal calculated |  | SQA-Agent-04
97 | M08-03 | Mark invoice as sent | M08-02 passed |  | 200 OK, status=sent |  | SQA-Agent-04
98 | M08-04 | Record payment against invoice | M08-03 passed |  | 201 Created, payment recorded |  | SQA-Agent-04
99 | M08-05 | Sales dashboard accessible to manager | Manager logged in |  | 200 OK |  | SQA-Agent-04
100 | M09-01 | Banking sector fields seeded (min 5) | Alpha Bank created |  | min 5 fields in custom_field_definitions |  | SQA-Agent-04
101 | M09-02 | account_number field exists | M09-01 passed |  | field name=account_number present |  | SQA-Agent-04
102 | M09-03 | Admin can add custom field | Admin logged in |  | 201 Created or 409 if exists |  | SQA-Agent-04
103 | M10-01 | Agent can delete own contact | Contact owned by agent |  | 204 No Content |  | SQA-Agent-04
104 | M10-02 | Deleted contact returns 404 | M10-01 passed |  | HTTP 404 |  | SQA-Agent-04
105 | SEC-01 | Brute force — 5 bad attempts triggers 429 lockout | Valid user exists |  | HTTP 429 after 5 failures |  | SQA-Agent-05
106 | SEC-02 | Tampered JWT (role escalation) rejected | Valid JWT obtained |  | HTTP 401/403 |  | SQA-Agent-05
107 | SEC-03 | Expired JWT (manipulated exp) rejected | Valid JWT obtained |  | HTTP 401/403 |  | SQA-Agent-05
108 | SEC-04a | Unauthenticated /contacts returns 401 | No token |  | HTTP 401 |  | SQA-Agent-05
109 | SEC-04b | Unauthenticated /tickets returns 401 | No token |  | HTTP 401 |  | SQA-Agent-05
110 | SEC-04c | Unauthenticated /deals returns 401 | No token |  | HTTP 401 |  | SQA-Agent-05
111 | SEC-04d | Unauthenticated /settings returns 401 | No token |  | HTTP 401 |  | SQA-Agent-05
112 | SEC-05 | Token invalid after logout (blocklist) | Valid JWT, logout called |  | HTTP 401 on reuse |  | SQA-Agent-05
113 | SEC-06 | Request without tenant context rejected | Valid JWT |  | HTTP 400+ |  | SQA-Agent-05
114 | SEC-07 | SQL injection in search param handled safely | Agent logged in |  | HTTP 200 or 400, no 500 |  | SQA-Agent-05
115 | SEC-08 | XSS payload in contact name handled (no 500) | Agent logged in |  | HTTP 200 or 400, no 500 |  | SQA-Agent-05
116 | SEC-09 | Extreme integer value handled (no 500) | Agent logged in |  | HTTP 200 or 400, no 500 |  | SQA-Agent-05
117 | SEC-10 | Empty required fields rejected (400/422) | Agent logged in |  | HTTP 400 or 422 |  | SQA-Agent-05
118 | SEC-11 | Agent cannot elevate own role (privilege escalation) | Agent logged in |  | HTTP 403 |  | SQA-Agent-05
119 | SEC-12 | Random UUID returns 404 (no info leakage) | Agent logged in |  | HTTP 404 |  | SQA-Agent-05
120 | SEC-13 | Alpha agent cannot delete Beta contact (IDOR) | Both banks created |  | HTTP 403 or 404 |  | SQA-Agent-05
121 | SEC-14 | Oversized payload rejected (no 500) | Agent logged in |  | HTTP 400/413, no 500 |  | SQA-Agent-05
122 | SEC-19 | Password < 10 chars rejected | API running |  | HTTP 400 |  | SQA-Agent-05
123 | SEC-20 | Password without uppercase rejected | API running |  | HTTP 400 |  | SQA-Agent-05
124 | SEC-21 | Password without lowercase rejected | API running |  | HTTP 400 |  | SQA-Agent-05
125 | SEC-22 | Password without special char rejected | API running |  | HTTP 400 |  | SQA-Agent-05
126 | UX-01 | Dashboard data returns within 2000ms | API running |  | Response time < 2000ms |  | SQA-Agent-05
127 | UX-02 | Contact list returns paginated structure | Agent logged in |  | Pagination meta present in response |  | SQA-Agent-05
128 | UX-03 | Contact search returns 200 (even 0 results) | Agent logged in |  | HTTP 200 |  | SQA-Agent-05
129 | UX-04 | Error responses follow consistent format | Invalid request made |  | {success:false, error:{code,message}} |  | SQA-Agent-05
130 | UX-05 | Errors do not expose stack traces | Invalid request made |  | No 'at Object' in response |  | SQA-Agent-05
131 | UX-06 | Swagger/OpenAPI docs accessible at /docs | API running |  | HTTP 200 or 301 |  | SQA-Agent-05
132 | UX-07 | Health check endpoint responds | API running |  | HTTP 200 |  | SQA-Agent-05
133 | UX-08 | Non-existent route returns 404 (not 500) | API running |  | HTTP 404 |  | SQA-Agent-05
134 | UX-09 | Contact create returns full object (not just ID) | Agent logged in |  | Response has 5+ fields |  | SQA-Agent-05
135 | UX-10 | CORS headers present (OPTIONS responds) | API running |  | No 500 on OPTIONS |  | SQA-Agent-05

## 🐛 Defect Log
Defect # | TC ID | Defect Description | Severity | Priority | Steps to Reproduce | Status | Assigned To | Date Found | Date Fixed

## 📋 Execution Log
Run # | Agent | Run Date | Environment | Total | Passed | Pass % | Notes

## 📦 Test Data
VIVID CRM — SQA TEST DATA REFERENCE
CATEGORY | VALUE | NOTES
── SERVICES ─────────────────────────────────────────────────────────────────
API Base URL | http://localhost:3000 | Dev environment
Frontend URL | http://localhost:5173 | Vite dev server
Swagger Docs | http://localhost:3000/docs | OpenAPI UI
DB Connection | postgresql://crm:crm_dev_password@localhost:5432/crm_platform | Dev DB
── SUPER ADMIN ──────────────────────────────────────────────────────────────
Super Admin Email | admin@demo.com | In demo workspace
Super Admin Password | Vivid@Solutions1 | Default dev credentials
Super Admin Slug | demo | Banking sector workspace
── ALPHA BANK (Full-featured) ───────────────────────────────────────────────
Slug | sqa-alpha-bank | Banking sector, Professional plan
Admin Email | admin@alpha-bank-sqa.com | Created by SQA Agent 01
Admin Password | Admin@Alpha2026! | Test credential
Modules | crm, ticketing, analytics, emails | Licensed by super admin
── BETA BANK (Limited) ──────────────────────────────────────────────────────
Slug | sqa-beta-bank | Banking sector, Starter plan
Admin Email | admin@beta-bank-sqa.com | Created by SQA Agent 01
Admin Password | Admin@Beta2026! | Test credential
Modules | crm, ticketing | Starter plan limitation
── TEST USERS (same password for all) ─────────────────────────────────────
Test Password | Test@CRM2026! | All invited users
Retail Manager | mgr.retail.[alpha¦beta]@sqa-vivid.com | role=manager
Retail Asst Mgr | am.retail.[alpha¦beta]@sqa-vivid.com | role=agent
Retail Executive | exec.retail.[alpha¦beta]@sqa-vivid.com | role=agent
Loans Manager | mgr.loans.[alpha¦beta]@sqa-vivid.com | role=manager
Support Manager | mgr.support.[alpha¦beta]@sqa-vivid.com | role=manager
Support Agent 1 | agent1.support.[alpha¦beta]@sqa-vivid.com | role=agent
Compliance Viewer | viewer.compliance.[alpha¦beta]@sqa-vivid.com | role=viewer
── PASSWORD POLICY ─────────────────────────────────────────────────────────
Min Length | 10 characters | BCRYPT cost 14
Requirements | Upper + Lower + Digit + Special | Enterprise policy
Lockout | 5 failed attempts → 15min lockout | Redis-backed